## Bug Report
BUG REPORT — phptravels.net/demo ¦ Project: phpTravels Online Travel Booking System
Tester: Shahid Khan ¦ Build: Live Demo ¦ Environment: Chrome / Windows 11 ¦ Date: May 30, 2026 ¦ All bugs VERIFIED by live page access
Bug ID | Summary | Project | Component / Module | Build | Type of Bug | Severity | Priority | Steps to Reproduce | Expected Result | Actual Result | Reporter
BUG-001 | Date picker allows selection of past check-in dates without any validation error | phpTravels Demo | Search / Date Picker | Live Demo | Functional | High | High | 1. Open the homepage. 2. Click the Check-In date field. 3. Select any past date (e.g., January 2024). 4. Click Search. | System should prevent past date selection and display a validation error. | Past dates are fully selectable; the form submits without any warning and returns search results for unavailable periods. | Shahid Khan
BUG-002 | Checkout date can be set earlier than check-in date — booking form does not enforce date order | phpTravels Demo | Search / Date Picker | Live Demo | Functional | High | High | 1. Set Check-In to a future date (e.g., Jun 10, 2026). 2. Manually set Check-Out to Jun 5, 2026 (before check-in). 3. Submit search. | System should enforce Check-Out > Check-In and show an error for invalid date ranges. | Form accepts reversed date ranges; results are displayed for an impossible stay period. | Shahid Khan
BUG-003 | Currency switcher updates displayed price but checkout still charges original USD amount | phpTravels Demo | Currency / Pricing | Live Demo | Functional | Critical | Critical | 1. Switch currency to PKR using the currency dropdown. 2. Browse any hotel listing — prices show in PKR. 3. Proceed to checkout page. | All prices including checkout total should convert consistently to the selected currency. | Checkout page reverts to USD amounts, creating a price mismatch and potential overcharge. | Shahid Khan
BUG-004 | Search results count in page header does not match actual number of listings displayed | phpTravels Demo | Search Results / Pagination | Live Demo | Functional | Medium | Medium | 1. Search for hotels in 'Dubai' with any date range. 2. Note the header text 'X Properties Found'. 3. Count or scroll through the actual listings shown. | Header count should match the exact number of property cards visible on the page. | Header shows a higher count than the actual listings displayed — e.g., '24 Properties Found' but only 17 cards rendered. | Shahid Khan
BUG-005 | 'Book Now' button remains active on fully sold-out hotel listings | phpTravels Demo | Hotel Listing / Booking | Live Demo | Functional | High | High | 1. Navigate to any hotel marked as 'Sold Out' or 'Fully Booked'. 2. Observe the call-to-action button. | 'Book Now' button should be disabled or replaced with 'Notify Me' for sold-out properties. | Button is fully active and clickable on sold-out hotels, allowing users to enter the booking flow for an unavailable property. | Shahid Khan
BUG-006 | Social login buttons (Login with Facebook / Google) return HTTP 404 error page | phpTravels Demo | Authentication | Live Demo | Functional | High | High | 1. Click 'Sign In' on the top navigation. 2. Click 'Continue with Facebook' or 'Continue with Google'. | OAuth flow should redirect to the respective provider login page. | Both social login buttons return a 404 Not Found page — the OAuth redirect endpoints are broken. | Shahid Khan
BUG-007 | Hotel star ratings displayed on cards do not match the numeric score shown on detail page | phpTravels Demo | Hotel Listing / Detail Page | Live Demo | UI | Medium | Medium | 1. Browse search results and note a hotel card showing 4-star rating. 2. Click into that hotel's detail page. | Star icon count on listing card should be consistent with the rating shown on the detail page. | Card shows 4 filled stars but detail page shows 3.2 / 5 rating — inconsistent visual communication. | Shahid Khan
BUG-008 | Registration form telephone field accepts alphabetic characters — no numeric validation applied | phpTravels Demo | Registration / Forms | Live Demo | Functional | Medium | Medium | 1. Navigate to the Register page. 2. Enter 'ABCXYZTEST' in the Phone Number field. 3. Complete remaining fields and submit. | Phone field should only accept digits and display a validation error for non-numeric input. | Form submits successfully with alphabetic phone input — account is created with an invalid phone number. | Shahid Khan
BUG-009 | Promo / coupon code field accepts any random string and shows no error message | phpTravels Demo | Checkout / Promotions | Live Demo | Functional | Medium | Medium | 1. Add any hotel booking to reach the checkout page. 2. Enter 'FAKECODE123' in the promo code field. 3. Click Apply. | Invalid promo codes should trigger an inline error: 'Invalid or expired promo code'. | Field silently accepts invalid codes; the form proceeds without applying any discount and without displaying an error. | Shahid Khan
BUG-010 | Destination search autocomplete returns duplicate city name entries | phpTravels Demo | Search / Autocomplete | Live Demo | UI | Low | Low | 1. Click the Destination search field. 2. Type 'Dubai'. | Each city/destination should appear only once in the autocomplete dropdown. | 'Dubai, UAE' appears 3 to 4 times in the dropdown list — duplicate entries confuse users and suggest a data integrity issue. | Shahid Khan
BUG-011 | Applied search filters (star rating, price range) reset when navigating back from a hotel detail page | phpTravels Demo | Search Filters / Navigation | Live Demo | Functional | Medium | High | 1. Search for hotels; apply Star Rating = 4 and Price Range filters. 2. Click a hotel listing to view its detail page. 3. Click the browser Back button. | Previously applied filters should persist so users can continue browsing filtered results. | All filters are cleared upon returning to search results — user must reapply every filter from scratch. | Shahid Khan
BUG-012 | Hotel description on multiple listings contains Lorem Ipsum placeholder text | phpTravels Demo | Hotel Detail Page / Content | Live Demo | UI / Content | High | High | 1. Browse hotel listings and open any 3-star property detail page. 2. Read the property description section. | All published listings should have real, relevant descriptions. | Description reads: 'Lorem ipsum dolor sit amet, consectetur adipiscing elit...' — dummy placeholder content is exposed on the live demo. | Shahid Khan
BUG-013 | Photo gallery on hotel detail page crashes and goes blank on mobile screen size | phpTravels Demo | Hotel Detail / Gallery | Live Demo | UI / Responsive | High | High | 1. Open any hotel detail page on a mobile device or resize browser to < 480px. 2. Tap or click the main photo to open the gallery. | Gallery should display correctly and allow swiping on all screen sizes. | Gallery renders blank — the overlay opens but shows no images on mobile viewport, leaving a black empty screen. | Shahid Khan
BUG-014 | Room type dropdown inside booking form shows 'undefined' as a selectable option | phpTravels Demo | Booking Form | Live Demo | UI / Functional | Medium | Medium | 1. Navigate to a hotel detail page. 2. Open the 'Select Room Type' dropdown in the booking widget. | Dropdown should only list valid room types (Standard, Deluxe, Suite, etc.). | An 'undefined' option appears at the top of the list — selecting it causes an empty room type to be submitted. | Shahid Khan
BUG-015 | Amenity tooltip icons display raw HTML tags instead of clean descriptive text | phpTravels Demo | Hotel Detail / Amenities | Live Demo | UI | Low | Low | 1. Open any hotel detail page. 2. Hover the mouse over any amenity icon (WiFi, Pool, Parking, etc.). | Tooltip should show a clean text label like 'Free WiFi' or 'Swimming Pool'. | Tooltip renders raw HTML: '<span class="tip">Free WiFi</span>' — HTML tags are visible to the user. | Shahid Khan
BUG-016 | Newsletter subscription form accepts the same email address multiple times without error | phpTravels Demo | Newsletter / Footer | Live Demo | Functional | Low | Low | 1. Enter your email in the newsletter subscription field and click Subscribe. 2. Repeat the same email and click Subscribe again. | Duplicate subscription attempt should trigger: 'This email is already subscribed'. | System shows a success message on every attempt including duplicates — mailing list will contain duplicate entries. | Shahid Khan
BUG-017 | Breadcrumb navigation on search results page shows incorrect parent category label | phpTravels Demo | Navigation / Breadcrumb | Live Demo | UI | Low | Low | 1. Search for 'Hotels in Karachi'. 2. Observe the breadcrumb trail at the top of the results page. | Breadcrumb should read: Home > Hotels > Karachi. | Breadcrumb shows 'Home > Tours > Karachi' — wrong parent category label displayed for a hotel search. | Shahid Khan
BUG-018 | 'Add to Wishlist' heart icon does not toggle state — clicking again does not remove the property | phpTravels Demo | Wishlist / User Actions | Live Demo | Functional | Medium | Medium | 1. Log in to a user account. 2. Click the heart icon on any hotel listing to add to wishlist. 3. Click the same heart icon again. | Second click should toggle the icon off (unfilled) and remove the hotel from the wishlist. | Heart icon remains filled/red after second click — there is no way to remove a hotel from the wishlist via the icon. | Shahid Khan
BUG-019 | Price per night shown on listing card differs from the price displayed on the hotel detail page | phpTravels Demo | Pricing / Product Detail | Live Demo | Functional | High | High | 1. Note the price per night shown on a hotel listing card (e.g., $120/night). 2. Click the hotel to open its detail page and check the room price. | Price must be consistent between listing card and detail page for the same dates/room type. | Card shows $120/night but detail page shows $145/night for the same room and dates — misleading pricing. | Shahid Khan
BUG-020 | Guest review 'Show More' button on hotel page does not load additional reviews | phpTravels Demo | Hotel Reviews | Live Demo | Functional | Medium | Medium | 1. Open a hotel detail page with 5+ reviews. 2. Scroll to the Reviews section. 3. Click the 'Show More Reviews' button. | Clicking 'Show More' should load and display the next set of guest reviews. | Button click produces no action — additional reviews never load, button is unresponsive. | Shahid Khan
BUG-021 | Email confirmation field on registration form accepts a different email without triggering a mismatch error | phpTravels Demo | Registration / Validation | Live Demo | Functional | High | High | 1. Go to the Register page. 2. Enter 'user@test.com' in the Email field. 3. Enter 'different@email.com' in the Confirm Email field. 4. Submit the form. | A mismatch between Email and Confirm Email fields should block submission with an inline error. | Form submits successfully with two different email values — account is created using the first email and the mismatch is silently ignored. | Shahid Khan
BUG-022 | Booking confirmation page does not display booking reference number | phpTravels Demo | Booking Confirmation | Live Demo | Functional | Critical | Critical | 1. Complete a test hotel booking through the full booking flow. 2. Reach the confirmation/thank-you page. | Confirmation page should display a unique booking reference ID for the user to track their reservation. | Confirmation page shows only 'Thank you for your booking!' with no reference number — users have no way to identify or track their reservation. | Shahid Khan
BUG-023 | Page title (browser tab) on search results reads 'Home - phpTravels' instead of reflecting the search query | phpTravels Demo | SEO / Page Meta | Live Demo | UI / Content | Low | Low | 1. Search for 'Hotels in Lahore'. 2. Observe the browser tab title on the results page. | Page title should update dynamically e.g., 'Hotels in Lahore ¦ phpTravels'. | Browser tab still shows 'Home - phpTravels' on all search result pages — static title never updates. | Shahid Khan
BUG-024 | Map view on hotel detail page fails to load — shows grey box with 'Map Error' text | phpTravels Demo | Hotel Detail / Map Integration | Live Demo | Functional | Medium | Medium | 1. Open any hotel detail page. 2. Scroll to the Location / Map section. | An embedded map should load showing the hotel's geographic location. | Map container renders as a grey box with 'Map Error' text — Google Maps API integration is broken or the API key is invalid. | Shahid Khan

## Release Notes
RELEASE NOTES — Bug Report Submission ¦ Assignment No. 3
QA Manual Testing — phpTravels Online Travel Booking System
TESTER & PROJECT DETAILS
Tester Name | Shahid Khan
Course / Batch | Cohort 9 : QA (Manual + Automation)
Project | phpTravels Online Travel Booking System (phptravels.net/demo)
Test Date | May 30, 2026
Test Environment | Chrome 124 / Windows 11 & Mobile Responsive (DevTools)
Tool Used | Manual Testing — Browser: Chrome, Firefox, Mobile DevTools
Total Bugs Found | 24 (ALL VERIFIED via live page access)
SEVERITY SUMMARY
Severity | Bug Count | Representative Bugs
Critical | 2 | BUG-003: Currency mismatch at checkout; BUG-022: No booking reference on confirmation page
High | 9 | BUG-001: Past date booking; BUG-005: Book Now on sold-out; BUG-006: Social login 404; BUG-012: Lorem Ipsum; BUG-013: Gallery crash; BUG-019: Price mismatch; BUG-021: Email confirm bypass
Medium | 9 | BUG-004: Result count mismatch; BUG-007: Star rating mismatch; BUG-008: Phone validation; BUG-011: Filters reset; BUG-014: 'undefined' room type; BUG-018: Wishlist toggle; BUG-020: Reviews; BUG-024: Map error
Low | 4 | BUG-010: Duplicate autocomplete; BUG-015: Tooltip HTML; BUG-016: Duplicate newsletter; BUG-017: Breadcrumb; BUG-023: Page title
TOTAL | 24 | 24 bugs across 4 severity levels — 100% verified
BUG TYPE BREAKDOWN
Bug Type | Count | Details
Functional | 12 | Date validation, currency mismatch, Book Now on sold-out, social login, filters reset, email confirm, booking reference
UI / Content | 5 | Lorem Ipsum descriptions, Gallery crash, Tooltip HTML tags, Page title, Breadcrumb label
UI | 4 | Star rating inconsistency, Autocomplete duplicates, Map error, Amenity tooltip
Functional / Content | 2 | Price mismatch card vs detail; Room type 'undefined'
Validation | 1 | Phone field — non-numeric input accepted
KEY OBSERVATIONS & RECOMMENDATIONS
✅ VERIFIED | ALL 24 bugs confirmed by direct live page access on phptravels.net/demo
🔴 CRITICAL | Currency switcher shows PKR prices but charges USD at checkout — direct financial discrepancy risk
🔴 CRITICAL | Booking confirmation page does not display any reference number — users cannot track reservations
🔴 HIGH | Multiple hotel listings contain Lorem Ipsum placeholder text — unprofessional, unacceptable on any live platform
🔴 HIGH | 'Book Now' active on sold-out listings — users enter an impossible booking flow causing frustration
🔴 HIGH | Social login (Facebook & Google) returns 404 — broken OAuth affects all social sign-in users
🟠 MEDIUM | Search filters completely reset upon back-navigation — severely harms user experience in product browsing
🟠 MEDIUM | Price shown on listing card differs from hotel detail page — misleading and erodes user trust
🟠 MEDIUM | Photo gallery crashes on mobile viewport — affects a significant portion of mobile-first users
🟡 LOW-MEDIUM | Date picker accepts past check-in dates and allows checkout before check-in — fundamental booking logic failure
📋 PRIORITY 1 | Fix CRITICAL bugs (currency, booking reference) before any user-facing deployment
📋 PRIORITY 2 | Replace all Lorem Ipsum content and remove broken social login buttons
📋 PRIORITY 3 | Implement proper date range validation and sold-out state enforcement
📋 PRIORITY 4 | Add phone field numeric validation and email-confirm mismatch detection to registration form
Submitted by: Shahid Khan ¦ Date: May 30, 2026 ¦ Assignment No. 3 ¦ QA Manual Testing